## PlanMatrix
Domains | Domains Code | Areas | Areas Code | Issues | Issues Code | Procedures | Procedures Code | Description
01. IT Governance | 01 | 01.01. Business Needs Identification, Direction and Monitoring | 01.01 | 01.01. 01. Defining IT requirements | 01.01. 01 | Assess whether the organization leadership effectively direct, evaluate and monitor IT use in the organization in order to fulfill the organization’s mission. | 01.01. 01.01 | How does the organization identify and approve business and IT requirements?
01. IT Governance | 01 | 01.01. Business Needs Identification, Direction and Monitoring | 01.01 | 01.01. 02. Leadership | 01.01. 02 | How does the leadership direct and monitor the performance of business and IT objectives on a periodic basis? | 01.01. 02.01 | Performance measures are established and the steering or equivalent high level committee conducts periodic reviews and meetings and takes appropriate action, or there is a reporting system to management that informs them of the status of key performance measures.
01. IT Governance | 01 | 01.01. Business Needs Identification, Direction and Monitoring | 01.01 | 01.01. 03. IT Investments | 01.01. 03 | Assess whether the organization leadership effectively direct, evaluate and monitor IT use in the organization in order to fulfill the organization’s mission. | 01.01. 03.01 | Organizations should manage their IT projects and investments in manner that maximizes benefits and considers elements such as risk, capabilities, needs, and prioritization among competing investments.
01. IT Governance | 01 | 01.02. IT Strategy and Planning | 01.02 | 01.02. 01. Quality of IT strategy | 01.02. 01 | Confirm whether there is an IT strategy in place, including the IT plan and the processes for the strategy’s development, approval, and implementation and maintenance which is aligned with the organization’s strategies and objectives. The risks and resources while accomplishing IT objectives are effectively managed. | 01.02. 01.01 | An organizational level IT strategic plan exists, it translates business objectives into IT goals and requirements, addresses the needed IT resources to support the business, it is reviewed and updated periodically.
01. IT Governance | 01 | 01.02. IT Strategy and Planning | 01.02 | 01.02. 02. Risk management | 01.02. 02 | Confirm whether there is an IT strategy in place, including the IT plan and the processes for the strategy’s development, approval, and implementation and maintenance which is aligned with the organization’s strategies and objectives. The risks and resources while accomplishing IT objectives are effectively managed. | 01.02. 02.01 | The organization has risk management policy and plan and has assigned sufficient resources to identify and manage risks.
01. IT Governance | 01 | 01.03. Organisational structures, Standards, Policies and Procedures | 01.03 | 01.03. 01. Structure of the IT Organization | 01.03. 01 | Ensure that there are organizational structures, policy, and procedures in place that enable the organization to meet their mandate for business goals, organization’s strategies and objectives. The risks and resources while accomplishing IT objectives are effectively managed. | 01.03. 01.01 | The IT Organization is positioned at a sufficiently high level within the organization and its roles and responsibilities are clearly defined including those of the Chief Information Officer (CIO) or equivalent.
01. IT Governance | 01 | 01.03. Organisational structures, Standards, Policies and Procedures | 01.03 | 01.03. 02. Policy and procedures | 01.03. 02 | Ensure that there are organizational structures, policy, and procedures in place that enable the organization to meet their mandate for business goals, organization’s strategies and objectives. The risks and resources while accomplishing IT objectives are effectively managed. | 01.03. 02.01 | The organization documents, approves, and communicates appropriate policies and procedures to guide business and IT operations in order to meet their mandate.
01. IT Governance | 01 | 01.04. People and Resources | 01.04 | 01.04. 01. HR and logistics | 01.04. 01 | To employ sufficiently qualified or trained personnel and have an access to suitable resources that enable the organization to meet their business goals. | 01.04. 01.01 | The organization should have a plan to meet their current and future requirements for meeting business needs.
01. IT Governance | 01 | 01.05. Risk Assessment and Compliance mechanisms | 01.05 | 01.05. 01. Mechanism | 01.05. 01 | How does the organization ensure that they have an adequate and working compliance mechanism to ensure all policies and procedures are being followed? | 01.05. 01.01 | The organization has a mechanism (via a QA group, internal audit, or spot check, etc.) to ensure that all policies and procedures are being followed.
02. IT Operations | 02 | 02.01. IT Service Continuity management | 02.01 | 02.01. 01. Key parameters | 02.01. 01 | To assess whether the IT organization is actively monitoring IT operations against agreed to internal Service Level Agreement or contract. | 02.01. 01.01 | SLA Best practices – allocation of responsibilities between the business process owners and the IT support group, documented network management business objectives, service offerings and metrics, definition for problem types, help desk responsibilities.
02. IT Operations | 02 | 02.01. IT Service Continuity management | 02.01 | 02.01. 02. Compliance | 02.01. 02 | To assess whether the IT organization is actively monitoring IT operations against agreed to internal Service Level Agreement or contract. | 02.01. 02.01 | SLA implemented, monitored and amended where necessary
02. IT Operations | 02 | 02.01. IT Service Continuity management | 02.01 | 02.01. 03. Effectiveness | 02.01. 03 | To assess whether the IT organization is actively monitoring IT operations against agreed to internal Service Level Agreement or contract. | 02.01. 03.01 | Achievement of performance metrics that are aligned to business needs and goals.
02. IT Operations | 02 | 02.02. Capacity Management | 02.02 | 02.02. 01. Agree to parameters | 02.02. 01 | Assess whether the IT organization is ensuring that the system capacity and performance meets current and future business needs. | 02.02. 01.01 | IT governance – track and monitor strategy implementation in terms of measurable metrics
02. IT Operations | 02 | 02.02. Capacity Management | 02.02 | 02.02. 02. Monitoring | 02.02. 02 | Assess whether the IT organization is ensuring that the system capacity and performance meets current and future business needs. | 02.02. 02.01 | Best practices by sys/network administrators like performance base lining, collection of traffic and configuration information, system resource availability, observe traffic stats and trends, what-if analyses, use of tools to pinpoint causes of performance deterioration.
02. IT Operations | 02 | 02.02. Capacity Management | 02.02 | 02.02. 03. Analyze and tune | 02.02. 03 | Assess whether the IT organization is ensuring that the system capacity and performance meets current and future business needs. | 02.02. 03.01 | Parameters set in the agreement/operation guide; best practices in performance tuning ( memory, optimization of network response time, OS, I/O, efficient design of database schema, scheduling tasks according to priority and resource requirement, upgrade or tuning procedures set up to handle capacity issues on both a reactive and long-term basis).
02. IT Operations | 02 | 02.03. Problem and incident management | 02.03 | 02.03. 01. Policy awareness | 02.03. 01 | To evaluate the effectiveness of organization’s problem and incident management policies and procedures. | 02.03. 01.01 | Best practices in incident response
02. IT Operations | 02 | 02.03. Problem and incident management | 02.03 | 02.03. 02. Skill sets and resources | 02.03. 02 | To evaluate the effectiveness of organization’s problem and incident management policies and procedures. | 02.03. 02.01 | Incidents response best practices, NIST guidelines, as laid down in SLA.
02. IT Operations | 02 | 02.03. Problem and incident management | 02.03 | 02.03. 03. Effectiveness of response | 02.03. 03 | To evaluate the effectiveness of organization’s problem and incident management policies and procedures. | 02.03. 03.01 | Incidents response best practices(COBIT 5 DSS Domain, ITIL on Service support).
02. IT Operations | 02 | 02.04. Change Management | 02.04 | 02.04. 01. Policy | 02.04. 01 | Assess whether the entity has implemented a standardized procedure for controlling all changes to the core IT systems and applications. | 02.04. 01.01 | Best practices in change controls: Request for change - authentication- acceptance - prioritization- change design –testing change - implementation- documentation.
02. IT Operations | 02 | 02.04. Change Management | 02.04 | 02.04. 02. Fallback procedures | 02.04. 02 | Assess whether the entity has implemented a standardized procedure for controlling all changes to the core IT systems and applications. | 02.04. 02.01 | Change Management best practices - documentation on procedures and responsibilities for recovery of affected areas due to undesirable change impact.
02. IT Operations | 02 | 02.04. Change Management | 02.04 | 02.04. 03. Emergency changes | 02.04. 03 | Assess whether the entity has implemented a standardized procedure for controlling all changes to the core IT systems and applications | 02.04. 03.01 | Emergency change management procedures. Documentation on change tests and implementation. Recovery documentation and configuration change logs. Backup and restore procedures.
02. IT Operations | 02 | 02.04. Change Management | 02.04 | 02.04. 04. Change closure and documentation | 02.04. 04 | Assess whether the entity has implemented a standardized procedure for controlling all changes to the core IT systems and applications | 02.04. 04.01 | Change management best practices (e.g. COBIT 5-BAI domain, ITIL on Service support)
03. Development and Acquisition | 03 | 03.01. Requirements Development and Management | 03.01 | 03.01. 01. Identify user requirements for IT Systems | 03.01. 01 | Assess how the organization identifies, prioritizes and manages their requirements for IT systems | 03.01. 01.01 | The organization has a plan or procedures on how to collect, review, and catalog requirements for new or added functionality
03. Development and Acquisition | 03 | 03.01. Requirements Development and Management | 03.01 | 03.01. 02. Analyze, prioritize, and manage user requirements | 03.01. 02 | Assess how the organization identifies, prioritizes and manages their requirements for IT systems. | 03.01. 02.01 | The organization analyzes, prioritizes, and manages requirements to ensure that user needs are met in an optimum and cost effective manner.
03. Development and Acquisition | 03 | 03.02. Project Management and Control | 03.02 | 03.02. 01. Plan for the development or acquisition of IT projects | 03.02. 01 | Assess how the organization manages and controls the development or acquisition of approved IT | 03.02. 01.01 | The organization analyzes, prioritizes, and manages requirements to ensure that user needs are met in an optimum and cost effective manner
03. Development and Acquisition | 03 | 03.02. Project Management and Control | 03.02 | 03.02. 02. Control IT projects | 03.02. 02 | Assess how the organization manages and controls the development or acquisition of approved IT | 03.02. 02.01 | The organization controls and tracks projects to ensure they meet their cost, schedule, and performance
03. Development and Acquisition | 03 | 03.02. Project Management and Control | 03.02 | 03.02. 03. Project related risk management | 03.02. 03 | Assess how the organization manages and controls the development or acquisition of approved IT | 03.02. 03.01 | Project management activities include managing project related risks and taking appropriate mitigations activities
03. Development and Acquisition | 03 | 03.03. Quality Assurance and Testing | 03.03 | 03.03. 01. Quality assurance organization | 03.03. 01 | Assess how the organization ensures that IT projects under development or acquisition meet their quality goals. | 03.03. 01.01 | An established procedure for conducting quality assurance activities.
03. Development and Acquisition | 03 | 03.03. Quality Assurance and Testing | 03.03 | 03.03. 02. Plan for and conduct testing on IT systems | 03.03. 02 | Assess how the organization ensures that IT projects under development or acquisition meet their quality goals. | 03.03. 02.01 | The organization conducts test on IT systems and based on the results accepts or rejects the system
03. Development and Acquisition | 03 | 03.04. Solicitation | 03.04 | 03.04. 01. Plan or procedure of solicitation activities | 03.04. 01 | Assess how the organization ensures that solicitation activities(set of tasks like firming up the need document, framing RFP, evaluating proposals, conducting pre-bid clarifications, designing and floating tender, evaluation, etc leading up to the award contract) are conducted in accordance with their adopted solicitation plan or procedure. | 03.04. 01.01 | Solicitation activities including vendor selection are conducted in accordance with the organization’s solicitation plan.
03. Development and Acquisition | 03 | 03.04. Solicitation | 03.04 | 03.04. 02. Selecting a vendor | 03.04. 02 | Assess how the organization ensures that solicitation activities(set of tasks like firming up the need document, framing RFP, evaluating proposals, conducting pre-bid clarifications, designing and floating tender, evaluation, etc leading up to the award contract) are conducted in accordance with their adopted solicitation plan or procedure. | 03.04. 02.01 | The organization uses objective and published criteria for vendor selection for each
03. Development and Acquisition | 03 | 03.05. Configuration Management | 03.05 | 03.05. 01. Policy for configuration management | 03.05. 01 | Assess how the organization manages configurations of work products related to development and acquisition. | 03.05. 01.01 | Configuration management activities are conducted according to the organizational policy or procedure
03. Development and Acquisition | 03 | 03.05. Configuration Management | 03.05 | 03.05. 02. Responsibility for authorizing changes | 03.05. 02 | Assess how the organization manages configurations of work products related to development and acquisition. | 03.05. 02.01 | Only authorized and approved changes should be introduced into the production environment
04. Outsourcing | 04 | 04.01. Outsourcing Policy | 04.01 | 04.01. 01. Policy on outsourcing | 04.01. 01 | To assess whether the agency has an adequate policy on outsourcing? | 04.01. 01.01 | Organizational policy on outsourcing
04. Outsourcing | 04 | 04.02. Solicitation | 04.02 | 04.02. 01. Policy on acquisition | 04.02. 01 | To assess whether the agency has a policy on how to manage solicitation | 04.02. 01.01 | Provisions of organization policy on Outsourcing and policy on IT services procurement dealing with solicitation and acquisition
04. Outsourcing | 04 | 04.03. Vendor or contract Management | 04.03 | 04.03. 01. Vendor or Contractor Monitoring | 04.03. 01 | To assess whether the organization is managing the contractor or vendor and takes appropriate action when performance or quality deviates from established baselines. | 04.03. 01.01 | Provisions/ parameters defined in Service Level Agreement and the follow up actions by the organization.
04. Outsourcing | 04 | 04.04. Data Rights | 04.04 | 04.04. 01. Data Rights | 04.04. 01 | To assess whether the organization’s data protection requirements are identified and they are part of the contractual requirements. | 04.04. 01.01 | Organization’s data protection and access rights requirements are levied on the contractor as appropriate
04. Outsourcing | 04 | 04.05. Overseas Service Provider | 04.05 | 04.05. 01. Overseas Service Provider | 04.05. 01 | To determine if the organization has strategy on contracting services to overseas vendors. | 04.05. 01.01 | Provisions of outsourcing policy related to outsourcing to overseas agencies. Laws of land regulating business with overseas agencies.
04. Outsourcing | 04 | 04.06. Retaining Business Knowledge | 04.06 | 04.06. 01. Retaining Business Knowledge | 04.06. 01 | To assess whether the agency retains business knowledge and ownership of business | 04.06. 01.01 | Organizations retain business knowledge and are able to continue operations in-house for mission critical function if contractors or vendors are unable to provide the service. Retention of business process ownership Retention of business knowledge. Performance vis a vis business continuity with respect to the service provider failing to provide service at any point.
04. Outsourcing | 04 | 04.07. Cost control and management | 04.07 | 04.07. 01. Cost control and management | 04.07. 01 | To assess whether the organization has ensured most economical cost | 04.07. 01.01 | The cost benefit analysis is realistic and is the basis to which the program is managed and controlled
04. Outsourcing | 04 | 04.08. Service Level Agreement | 04.08 | 04.08. 01. Service Level Agreement | 04.08. 01 | To assess whether the agency has developed the service level agreement | 04.08. 01.01 | The service level agreement is the basis for monitoring and controlling the contractor or vendor against technical and other requirements
04. Outsourcing | 04 | 04.09. Security | 04.09 | 04.09. 01. Identified security requirements | 04.09. 01 | To assess whether the security requirements are addressed in outsourcing and being complied to | 04.09. 01.01 | The organizations pertinent security requirements are levied on the contractor as appropriate
04. Outsourcing | 04 | 04.10. Back up and disaster recovery for outsourced services | 04.10 | 04.10. 01. Back up and disaster recovery for outsourced services | 04.10. 01 | To assess whether outsourced services adhere to business continuity and disaster recovery plans as required in the contract or service level agreement. | 04.10. 01.01 | Contractual or service level agreement for BCP and DRP at the vendor.
05. Information and Cyber Security | 05 | 05.01. Risk Assessment | 05.01 | 05.01. 01. Assessment Mechanism | 05.01. 01 | To ensure that all risks associated to cyber and information security has been identified and an appropriate risk mitigation strategy is put in place | 05.01. 01.01 | Organization prepared to manage critical risks (internal policy, procedures or regulations).
05. Information and Cyber Security | 05 | 05.01. Risk Assessment | 05.01 | 05.01. 02. Coverage | 05.01. 02 | To ensure that all risks associated to information security has been identified and an appropriate risk mitigation strategy is put in place. | 05.01. 02.01 | All the significant risks are identified and assessed properly (best practices in risk assessment).
05. Information and Cyber Security | 05 | 05.01. Risk Assessment | 05.01 | 05.01. 03. Mitigation | 05.01. 03 | To ensure that all risks associated to information security has been identified and an appropriate risk mitigation strategy is put in place | 05.01. 03.01 | Adequate risk mitigation practices are in place.
05. Information and Cyber Security | 05 | 05.02. Security Policy | 05.02 | 05.02. 01. Information Security Policy | 05.02. 01 | To assess whether there is adequate strategic direction and support for information security in terms of a security policy, its coverage, organization-wide awareness and compliance. | 05.02. 01.01 | The organization’s information security policy covers all operational risks and is able to reasonably protect all business critical information assets from loss, damage or abuse (Ref:ISO 27000 series Information Security Management System and other internal policy, procedures or applicable regulations).
05. Information and Cyber Security | 05 | 05.02. Security Policy | 05.02 | 05.02. 02. Confidentiality | 05.02. 02 | To assess whether there is adequate strategic direction and support for Cyber and information security in terms of a security policy, its coverage, organization-wide awareness and compliance. | 05.02. 02.01 | The organization has a plan on how they identify emerging business or IT needs and the Steering Committee approving requirements has sufficient information to make their decisions.
05. Information and Cyber Security | 05 | 05.03. Organisation of IT Security | 05.03 | 05.03. 01. Structure | 05.03. 01 | To ensure the secure operation of IT processing facilities. | 05.03. 01.01 | Clear IT roles and responsibilities relating to Information Security Policy (Ref: ISO 27000 series).
05. Information and Cyber Security | 05 | 05.03. Organisation of IT Security | 05.03 | 05.03. 02. Coordination | 05.03. 02 | To ensure the secure operation of IT processing facilities. | 05.03. 02.01 | No responsibility conflicts, disharmony nor “no-man’s land” in Information Security activities (Ref: ISO 27000 series Information Security Management System).
05. Information and Cyber Security | 05 | 05.03. Organisation of IT Security | 05.03 | 05.03. 03. Cybersecurity Organization | 05.03. 03 | To ensure critical infrastructure is adequately protected. | 05.03. 03.01 | Having a clear understanding of your organization’s mission, resources, risks, and how to safeguard them. Baldrige Cybersecurity Excellence Builder, V1.0, March 2017, pg. 6.
05. Information and Cyber Security | 05 | 05.04. Communications and Operations Management | 05.04 | 05.04. 01. Policy and procedures | 05.04. 01 | To ensure that internal and external communication and other interfaces are secure. | 05.04. 01.01 | The policy and procedures form stable management environment for internal and external communication. (Ref: ISO-27002, S15-IT Control (ISACA Standard), COBIT). Implementing Cybersecurity strategy (Baldridge Excellence Builder, V1.0, March 2017, pg 13).
05. Information and Cyber Security | 05 | 05.04. Communications and Operations Management | 05.04 | 05.04. 02. Network control and Cybersecurity Monitoring | 05.04. 02 | To ensure that internal and external communication is secure. | 05.04. 02.01 | Network operations are managed, performed, and measured in an effective way. (Ref: ISO-27002, S15-IT Control (ISACA Standard), COBIT). Baldridge Excellece Builder, V1.0, March 2017, pg 16.
05. Information and Cyber Security | 05 | 05.04. Communications and Operations Management | 05.04 | 05.04. 03. Configuration Management | 05.04. 03 | To ensure that internal and external communication is secure. | 05.04. 03.01 | Clear and well managed configuration system that supports Information Security in communication
05. Information and Cyber Security | 05 | 05.05. Asset Management | 05.05 | 05.05. 01. Assets Management | 05.05. 01 | To encourage appropriate protection of IT assets | 05.05. 01.01 | Ensuring appropriate protection of information assets (Ref: ISO 2700 series Information Security Management System, COBIT, and other internal policy, procedures or regulations applied).
05. Information and Cyber Security | 05 | 05.06. Human Resources IT Security | 05.06 | 05.06. 01. Staff Awareness and Responsibility | 05.06. 01 | To ensure that all employees (including contractors and any user of sensitive data or the IT Systems where they reside) are qualified for data handling, use of IT resources, and understand their roles and responsibilities , and that access is removed once employment/ contract is terminated, and periodic refresher training is provided. | 05.06. 01.01 | Staff from recruitment to termination guards Information Security. Weaknesses in the staff’s professional approach do not jeopardize the organization’s information safety.
05. Information and Cyber Security | 05 | 05.06. Human Resources IT Security | 05.06 | 05.06. 02. Training | 05.06. 02 | To ensure that all employees (including contractors and any user of sensitive data or those that have access to corporate IT systems or infrastructure) are qualified for data handling and appropriate us if IT resources, and understand their roles and responsibilities, and that access is removed once employment/ contract is terminated. | 05.06. 02.01 | Trainings which provide proper skills and knowledge to employees whose role in the organization is significant for Information and Cybersecurity.
05. Information and Cyber Security | 05 | 05.07. Intrusion Detection and Protection | 05.07 | 05.07. 01. Premises safety | 05.07. 01 | To prevent theft or damage of IT hardware, unauthorized access, detecting cyber intrusion, and the copying or viewing of sensitive information. | 05.07. 01.01 | Ensure that physical and environmental security stays in compliance with the safety requirements and sensitivity classification of IT assets. Ensure tools and procedures are in place to monitor cyber activity and take appropriate actions.
05. Information and Cyber Security | 05 | 05.07. Intrusion Detection and Protection | 05.07 | 05.07. 02. Physical access | 05.07. 02 | To prevent theft or damage of IT hardware, unauthorized access, and copying or viewing of sensitive information. | 05.07. 02.01 | Ensure that organizational and physical measures ensure no unauthorized access.
05. Information and Cyber Security | 05 | 05.07. Intrusion Detection and Protection | 05.07 | 05.07. 03. Intrusion defense | 05.07. 03 | To prevent theft or damage of IT hardware, unauthorized access, and copying or viewing of sensitive information. | 05.07. 03.01 | Ensure that intrusions were and will be detected and combated (Internal security policy)
05. Information and Cyber Security | 05 | 05.08. Access Control | 05.08 | 05.08. 01. Access policy | 05.08. 01 | To ensure that only authorized users have access to relevant information | 05.08. 01.01 | The Access Policy gives sound basis for control of relevant information distribution.
05. Information and Cyber Security | 05 | 05.08. Access Control | 05.08 | 05.08. 02. Privileges management | 05.08. 02 | To ensure that only authorized users have access to relevant information. | 05.08. 02.01 | The Information Security function monitors the control effectiveness of user account management operations on a timely basis and reports the operating efficiency and effectiveness.
06. BCP-DRP | 06 | 06.01. Business Continuity Policy, Plan and Organisation | 06.01 | 06.01. 01. Contingency plan and policy for business continuity | 06.01. 01 | To assess whether there is an effective business continuity policy in the organization | 06.01. 01.01 | Organizational policy on business continuity containing roles and responsibilities, scope, resource allocation criteria/ principles, training requirements, maintenance schedule, testing schedule, back up plans etc and approval levels and related parties. Alternative: The organization has a published contingency plan and policy in place which comprehensively covers all areas of contingency operations and clearly identifies training requirements and testing schedule.
06. BCP-DRP | 06 | 06.02. Establishment of Business Continuity Function | 06.02 | 06.02. 01. Business continuity team or equivalent function | 06.02. 01 | To assess whether there is an effective business continuity policy in the organization. | 06.02. 01.01 | Coverage of all critical areas of the organization in the team. Roles and responsibility requirements for the team.
06. BCP-DRP | 06 | 06.03. Business Impact Assessment and Risk Management | 06.03 | 06.03. 01. Business impact and risk assessments | 06.03. 01 | To assess whether the business impact assessment and risk assessment have been completed and a risk management process is in place | 06.03. 01.01 | Enterprise Risk Management framework; Business Continuity Policy; Completion of the Business Impact Assessment and identification of critical data; application software; operations and resources.
06. BCP-DRP | 06 | 06.03. Business Impact Assessment and Risk Management | 06.03 | 06.03. 02. Risk management process | 06.03. 02 | To assess whether the business impact assessment and risk assessment have been completed and a risk management process is in place. | 06.03. 02.01 | Coverage of the risk management process vis a vis risk assessment and business impact assessment. Risks and emergencies are promptly addressed as per organization’s decided parameters.
06. BCP-DRP | 06 | 06.04. Preventive and environmental controls | 06.04 | 06.04. 01. Environment control mechanism | 06.04. 01 | To assess whether the organization has suitable environment control at back up sites. | 06.04. 01.01 | Environment control parameters in the environment control mechanism.
06. BCP-DRP | 06 | 06.05. Disaster Recovery Plan | 06.05 | 06.05. 01. Data and program back up procedures | 06.05. 01 | To assess whether the Business Continuity Plan includes backup and recovery plans for hardware, data, application software and data centre (recovery) and has been suitably implemented? | 06.05. 01.01 | Criticality of applications and functions as per Business Impact Assessment. Determined periodicity of backups. Documented backup and recovery plans.
06. BCP-DRP | 06 | 06.06. Testing | 06.06 | 06.06. 01. Testing the BCP and DRP | 06.06. 01 | To assess whether the business continuity and disaster recovery procedures have been tested. | 06.06. 01.01 | The organization should test their documented BCP and DRP procedures via drills or mock ups to ensure that they work in an actual conditions. Personnel involved in ensuring continuity should be aware of their roles.
06. BCP-DRP | 06 | 06.07. Security | 06.07 | 06.07. 01. Data, application software, hardware and data centre are secured | 06.07. 01 | To assess whether business continuity plan and disaster recovery plan ensures security of data, application software, hardware and data center | 06.07. 01.01 | Security baselines for the organization
06. BCP-DRP | 06 | 06.08. Back-up and data recovery for outsourced services | 06.08 | 06.08. 01. Outsourced service provider ensures BCP and DRP | 06.08. 01 | To assess whether outsourced services adhere to business continuity and disaster recovery plans. | 06.08. 01.01 | Security baselines for the organization.
07. Application Controls | 07 | 07.01. Input Controls | 07.01 | 07.01. 01. Adequate input validation controls | 07.01. 01 | to assess whether valid data is being entered into the application by authorized personnel | 07.01. 01.01 | Validation rules have been well designed, documented and implemented into the application entry interfaces; different methods and interfaces for data entry are documented; invalid data is properly rejected by the application; the validation criteria is updated in a timely, appropriate and authorized manner; there are compensating controls such as logs and authorization rules in case of the possibility of overriding input controls; there are proper controls and documentation for the application interfaces.
07. Application Controls | 07 | 07.01. Input Controls | 07.01 | 07.01. 02. Management of source documents, data collection and entry | 07.01. 02 | to assess whether valid data is being entered into the application by authorized personnel | 07.01. 02.01 | The data preparation procedures are documented and understood by users; there is appropriate logging and records of the source documents received until their disposal; there is assignment of unique and sequential numbers to each transaction; original source documents are retained for the time required by legal standards or policies.
07. Application Controls | 07 | 07.01. Input Controls | 07.01 | 07.01. 03. Adequate procedures for error handling | 07.01. 03 | to assess whether valid data is being entered into the application by authorized personnel | 07.01. 03.01 | There is a system of clear and compact error messages communicating the problems so that immediate corrective action can be taken for each type of error. Errors are corrected or appropriately overridden before processing transactions. Logs are reviewed periodically and necessary corrective action is taken.
07. Application Controls | 07 | 07.01. Input Controls | 07.01 | 07.01. 04. Management of data entry authorization into the application | 07.01. 04 | to assess whether valid data is being entered into the application by authorized personnel | 07.01. 04.01 | Authorization levels for transactions were established and are enforced by proper controls; there is proper segregate of duties for data entry; there are compensating controls in place for those cases in which segregation of duties is not possible.
07. Application Controls | 07 | 07.02. Processing Controls | 07.02 | 07.02. 01. Mapping the business processes rules and requirements | 07.02. 01 | To assess whether the application ensure data integrity, validity and reliability throughout the transaction processing cycle | 07.02. 01.01 | Application transactions run accordingly to the expected behavior
07. Application Controls | 07 | 07.02. Processing Controls | 07.02 | 07.02. 02. Application controls | 07.02. 02 | To assess whether the application ensure data integrity, validity and reliability throughout the transaction processing cycle | 07.02. 02.01 | The application does correctly identify transactional errors. Data integrity is maintained even during unexpected interruptions to transaction processing. There is an adequate mechanism for handling processing errors, review of suspense files and clearance.
07. Application Controls | 07 | 07.03. Output Controls | 07.03 | 07.03. 01. Assessment of application | 07.03. 01 | Assess whether application assures that output information is complete and accurate before further use and that it is properly protected | 07.03. 01.01 | Procedures have been designed to ensure that the completeness and accuracy of application output are validated prior to the output being used for subsequent processing, including use in end-user processing; tracking of application output is properly enabled; output is reviewed for reasonableness and accuracy; completeness and accuracy controls are effective.
07. Application Controls | 07 | 07.03. Output Controls | 07.03 | 07.03. 02. Output data properly protected | 07.03. 02 | Assess whether application assures that output information is complete and accurate before further use and that it is properly protected. | 07.03. 02.01 | Output is handled in line with the applicable confidentiality classification; distribution of outputs/ reports are appropriately controlled
07. Application Controls | 07 | 07.04. Application security controls | 07.04 | 07.04. 01. Traceability mechanisms | 07.04. 01 | Assess whether application’s information is properly secured against misuse | 07.04. 01.01 | There are audit trails which capture edits, overrides, and authorization logs to critical transactions; the audit trails are periodically reviewed to monitor unusual activity; the audit trail is adequately maintained and protected; unique and sequential numbers or identifiers are assigned to every transaction.
07. Application Controls | 07 | 07.04. Application security controls | 07.04 | 07.04. 02. Application data properly protected | 07.04. 02 | Assess whether application’s information is properly secured against misuse. | 07.04. 02.01 | For physical and logical access control refer to Appendix VII on Information Security. For disaster recovery planning refer to Appendix VI on BCP/DRP.